## Sheet1
Sprint | User Story/Tasks ID | User Story/Tasks | Acceptance Criteria | Status
0 | 0.1 | As a developer, I want to research and understand the immigration document requirements (I-20, I-94), so that I can build the necessary parsing functionality. | Clear understanding of I-20 and I-94 document structures. Document key fields that need to be parsed (e.g., Name, DoB, Visa Status). | Completed
0 | 0.2 | As a developer, I want to set up the development environment and tech stack, so that the team can start building the application. | Development environment is set up (Python, Flask, AI frameworks). Shared repository for the team to collaborate. | Completed
1 | 1.1 | As an International Student, I want to upload my I-20 document, so that I can view my basic information (Name, Date of Birth). | User can upload an I-20 PDF from the web interface. The system extracts and displays Name and Date of Birth. | Completed
1 | 1.2 | As a developer, I want to implement the PDF upload functionality on the frontend and backend, so that students can upload their documents. | Users can upload PDFs from the frontend. The backend processes uploaded documents. | Completed
1 | 1.3 | As a developer, I want to implement basic parsing functionality for I-20 documents, so that key fields (Name, DoB) can be extracted. | System parses I-20 documents and extracts Name and Date of Birth. Extracted information is displayed in the frontend user interface. | Completed
1 | 1.4 | As a developer, I want to ensure the application has error handling during the document upload process, so that users receive appropriate feedback for failed uploads. | Clear error messages for upload issues (e.g., wrong file type, corrupted file). The system logs errors for troubleshooting. | Completed
1 | 1.5 | As a developer, I want to set up the basic structure of the Flask backend, so that I can manage file uploads and communication between the frontend and backend. | Flask is set up with routes for handling file uploads. The backend communicates with the frontend for document uploads. | Completed
2 | 2.1 | As a developer, I want to collect immigration-related documents, so that the team can use them to provide personalized advice. | USCIS documents are collected. Common immigration-related Q&A are compiled. | Completed
2 | 2.2 | As a developer, I want to implement a tagging system, so that we have a structure to sort all the AI training materials which can train AI to provide personalized responses. | Materials are systematically identified and tagged. Document data is centralized and mapped to relevant questions accurately. | Completed
2 | 2.3 | As a developer, I want to develop an AI model (using BERT or an RNN), so that the system can handle user queries and deliver accurate responses. | AI model is trained on a dataset of immigration-related queries and document data. Model achieves an acceptable accuracy threshold in query-response testing. | Completed
2 | 2.4 | As a International Student,, I want to input immigration-related questions or queries into the system, so that I can receive tailored advice. | Users can input and submit queries through the system. Queries are processed and mapped to relevant responses or document data. | Completed
2 | 2.5 | As a International Student, I want a chatbox on the frontend where I can interact with the Immigration AI Advisor, so that I can easily ask questions and receive responses. | Chatbox is functional and user-friendly. Integrated with backend systems to process queries and display responses. | Completed
3 | 3.1 | As a developer, I want to verify the performance of the vector database so that the AI Advisor retrieves accurate and efficient search results for immigration-related queries. | The vector database achieves at least 95% accuracy, responds in under 200ms and passes load testing without crashes. | Completed
3 | 3.2 | As a International Student,, I want the front-end to display AI-generated summaries of my immigration documents so that I can quickly understand the key points of my I-20. | AI summaries are displayed correctly for 90% of uploaded documents, the design is responsive, and summaries refresh with a single click. | Completed
3 | 3.3 | As a developer, I want the system to be optimized for performance and efficiency so that users experience faster processing times and smoother interactions. | AI outputs load in under 5 seconds, memory usage is stable over 24 hours, and database query times improve by 30%. | Completed
3 | 3.4 | As a developer, I want to generate metrics on AI accuracy so that I can measure the system’s performance and improve weak areas. | Accuracy metrics exceed 85% for standard tests, are displayed on a dashboard, and logs capture all failed cases. | Completed
3 | 3.5 | As a International Student, I want pre-programmed immigration answers via the UI so that I can get instant responses to common queries. | Pre-programmed responses load in under 1 second for all queries, and 90% of users rate the responses as helpful. | Completed
3 | 3.6 | As a International Student, I want AI-generated immigration answers via the UI so that I can get dynamic responses to complex queries. | AI-generated answers load in under 3 seconds for all valid queries, and 90% of users rate the responses as helpful. | Not Completed
3 | 2.6 | As a developer, I want to fine-tune the AI model, so that it delivers more accurate and high-quality responses to user queries. | Fine-tuned model achieves higher performance metrics compared to the baseline. Improvements are documented and validated against test cases. | Not Completed

## Sheet3
Sprint | User Story/Tasks ID | User Story/Tasks | Acceptance Criteria | Status
0 | 0.1 | As a developer, I want to research and understand the immigration document requirements (I-20, I-94), so that I can build the necessary parsing functionality. | Clear understanding of I-20 and I-94 document structures. Document key fields that need to be parsed (e.g., Name, DoB, Visa Status). | Completed
0 | 0.2 | As a developer, I want to set up the development environment and tech stack, so that the team can start building the application. | Development environment is set up (Python, Flask, AI frameworks). Shared repository for the team to collaborate. | Completed
1 | 1.1 | As an International Student, I want to upload my I-20 document, so that I can view my basic information (Name, Date of Birth). | User can upload an I-20 PDF from the web interface. The system extracts and displays Name and Date of Birth. | Completed
1 | 1.2 | As a developer, I want to implement the PDF upload functionality on the frontend and backend, so that students can upload their documents. | Users can upload PDFs from the frontend. The backend processes uploaded documents. | Completed
1 | 1.3 | As a developer, I want to implement basic parsing functionality for I-20 documents, so that key fields (Name, DoB) can be extracted. | System parses I-20 documents and extracts Name and Date of Birth. Extracted information is displayed in the frontend user interface. | Completed
1 | 1.4 | As a developer, I want to ensure the application has error handling during the document upload process, so that users receive appropriate feedback for failed uploads. | Clear error messages for upload issues (e.g., wrong file type, corrupted file). The system logs errors for troubleshooting. | Completed
1 | 1.5 | As a developer, I want to set up the basic structure of the Flask backend, so that I can manage file uploads and communication between the frontend and backend. | Flask is set up with routes for handling file uploads. The backend communicates with the frontend for document uploads. | Completed
2 | 2.1 | As a developer, I want to collect immigration-related documents, so that the team can use them to provide personalized advice. | USCIS documents are collected. Common immigration-related Q&A are compiled. | Completed
2 | 2.2 | As a developer, I want to implement a tagging system, so that we have a structure to sort all the AI training materials which can train AI to provide personalized responses. | Materials are systematically identified and tagged. Document data is centralized and mapped to relevant questions accurately. | Completed
2 | 2.3 | As a developer, I want to develop an AI model (using BERT or an RNN), so that the system can handle user queries and deliver accurate responses. | AI model is trained on a dataset of immigration-related queries and document data. Model achieves an acceptable accuracy threshold in query-response testing. | Completed
2 | 2.4 | As a user, I want to input immigration-related questions or queries into the system, so that I can receive tailored advice. | Users can input and submit queries through the system. Queries are processed and mapped to relevant responses or document data. | Completed
2 | 2.5 | As a user, I want a chatbox on the frontend where I can interact with the Immigration AI Advisor, so that I can easily ask questions and receive responses. | Chatbox is functional and user-friendly. Integrated with backend systems to process queries and display responses. | Completed
2 | 2.6 | As a developer, I want to fine-tune the AI model, so that it delivers more accurate and high-quality responses to user queries. | Fine-tuned model achieves higher performance metrics compared to the baseline. Improvements are documented and validated against test cases. | Not Completed
3 | 3.1 | As the VP of Global Services, I want access to system-wide reports on document uploads and advice generation, so that I can evaluate the system’s impact on student advising. | Admins can access reports that track system usage, including document processing and AI advice provided. | Not Completed
3 | 3.2 | As a developer, I want to ensure the AI component provides detailed and accurate immigration advice, so that users receive tailored information based on multiple documents. | AI is enhanced to handle complex immigration queries. AI-generated advice reflects details from both I-20 and I-94 documents. | Not Completed
3 | 3.3 | As an Adviser, I want to receive notifications when students upload documents, so that I can assist them in a timely manner. | Advisers receive notifications when new documents are uploaded. Notifications include student details and document types. | Not Completed
3 | 3.4 | As a System Administrator, I want to ensure that the system has proper error handling and logging, so that any issues during document uploads or AI processing are captured and resolved quickly. | All system errors during uploads or processing are logged. Admins can view logs to troubleshoot issues. | Not Completed