## Sheet1
Sprint | User Story/Tasks ID | User Story/Tasks | Acceptance Criteria | Status
0 | 0.1 | As a developer, I want to research and understand the immigration document requirements (I-20, I-94), so that I can build the necessary parsing functionality. | Clear understanding of I-20 and I-94 document structures. Document key fields that need to be parsed (e.g., Name, DoB, Visa Status). | Completed
0 | 0.2 | As a developer, I want to set up the development environment and tech stack, so that the team can start building the application. | Development environment is set up (Python, Flask, AI frameworks). Shared repository for the team to collaborate. | Completed
1 | 1.1 | As an International Student, I want to upload my I-20 document, so that I can view my basic information (Name, Date of Birth). | User can upload an I-20 PDF from the web interface. The system extracts and displays Name and Date of Birth. | Completed
1 | 1.2 | As a developer, I want to implement the PDF upload functionality on the frontend and backend, so that students can upload their documents. | Users can upload PDFs from the frontend. The backend processes uploaded documents. | Completed
1 | 1.3 | As a developer, I want to implement basic parsing functionality for I-20 documents, so that key fields (Name, DoB) can be extracted. | System parses I-20 documents and extracts Name and Date of Birth. Extracted information is displayed in the frontend user interface. | Completed
1 | 1.4 | As a developer, I want to ensure the application has error handling during the document upload process, so that users receive appropriate feedback for failed uploads. | Clear error messages for upload issues (e.g., wrong file type, corrupted file). The system logs errors for troubleshooting. | Completed
1 | 1.5 | As a developer, I want to set up the basic structure of the Flask backend, so that I can manage file uploads and communication between the frontend and backend. | Flask is set up with routes for handling file uploads. The backend communicates with the frontend for document uploads. | Completed
2 | 2.1 | As a developer, I want to collect immigration-related documents, so that the team can use them to provide personalized advice. | USCIS documents are collected. Common immigration-related Q&A are compiled. | Completed
2 | 2.2 | As a developer, I want to implement a tagging system, so that we have a structure to sort all the AI training materials which can train AI to provide personalized responses. | Materials are systematically identified and tagged. Document data is centralized and mapped to relevant questions accurately. | Completed
2 | 2.3 | As a developer, I want to develop an AI model (using BERT or an RNN), so that the system can handle user queries and deliver accurate responses. | AI model is trained on a dataset of immigration-related queries and document data. Model achieves an acceptable accuracy threshold in query-response testing. | Completed
2 | 2.4 | As a user, I want to input immigration-related questions or queries into the system, so that I can receive tailored advice. | Users can input and submit queries through the system. Queries are processed and mapped to relevant responses or document data. | Completed
2 | 2.5 | As a user, I want a chatbox on the frontend where I can interact with the Immigration AI Advisor, so that I can easily ask questions and receive responses. | Chatbox is functional and user-friendly. Integrated with backend systems to process queries and display responses. | Completed
2 | 2.6 | As a developer, I want to fine-tune the AI model, so that it delivers more accurate and high-quality responses to user queries. | Fine-tuned model achieves higher performance metrics compared to the baseline. Improvements are documented and validated against test cases. | Not Completed
3 | 3.1 | Generate text responses based on query and knowledge base | The system generates accurate, coherent, and context-aware text responses. Responses are relevant to the query and align with the knowledge base. Handles queries outside the knowledge base gracefully by providing appropriate feedback or a fallback response. | Not Completed
3 | 3.2 | Improve semantic search | Semantic search returns the most contextually relevant results for user queries. Latency for search results is minimized and consistent. Improved precision and recall metrics for search functionality are documented. | Not Completed
3 | 3.3 | Clean up database (look at "extracted_text" field/column in Firebase, clean up) | The extracted_text field/column is normalized and free from redundant or irrelevant data. All unnecessary or malformed entries in Firebase are removed. The cleaned database supports efficient queries and ensures consistency across records. | Not Completed
3 | 3.4 | Improve tokenization and segmentation methods (use something more state-of-the-art) | Tokenization and segmentation methods reduce errors in text parsing and analysis. Benchmarked against baseline methods with measurable improvements in performance. Integrated seamlessly into the existing AI pipeline without causing regressions. | Not Completed
3 | 3.5 | Support users (login/auth) | Users can register and log in securely. Authentication is implemented with industry-standard practices (e.g., OAuth, JWT). User roles (e.g., admin, student) are defined and enforced within the application. | Not Completed
3 | 3.6 | Store user documents/contents | Uploaded user documents are securely stored in a database or cloud storage. Documents are tagged and indexed for efficient retrieval. Document storage complies with relevant privacy and data protection standards (e.g., GDPR, CCPA). | Not Completed
3 | 3.7 | Response to queries based on existing functionality, but incorporating user-uploaded documents | The system uses user-uploaded documents to generate tailored responses. Queries are processed to include relevant context from the uploaded documents. Provides accurate and personalized advice based on document data. | Not Completed
3 | 3.8 | Deploy a free, private demo version to web | A demo version of the application is deployed to a web server. Users can interact with core functionalities (e.g., upload documents, ask queries). Demo is secured to prevent unauthorized access and data leaks. | Not Completed